LIFELONG LEARNING PROGRAMME

LEONARDO DA VINCI

TRANSFER OF INNOVATION

PARTNER'S CONTRACT

PROJECT: TITLE

PROJECT NUMBER: LLP-LDV-TOI-2009-SI-##/09-####

Naziv in naslov koordinatorske organizacije

as follows “the coordinator”

represented by

Uradni predstavnik

and

Naziv in naslov partnerske organizacije

as follows “partner”

Represented by:

Uradni predstavnik

agree to sign the following

CONTRACT številka pogodbe

1. Article – Project title and period

The purpose of this contract is to fulfill the obligations by the coordinator and partner on the Leonardo da Vinci project naslov projekta, which was selected in the course of initiative Transfer of innovation, represented by national agency CMEPIUS, Center za mobilnost in evropske programe izobraževanja in usposabljanja.

The official period for project execution is: od -  do with tasks and deadlines in accordance with article 3 of this contract.

2. Article - Activities

Partner agrees to join project's consortium to perform the following main scopes of activities:

- Nanizane aktivnosti, če relevantno s časovno dinamiko

Partner is obligated to perform additional activities if this is necessary for the achievement of project goals and is in compliance with partners financial, human and other resources.

Partner must report to the project coordinator on a monthly basis (latest by 10th day in the month for the previous month) on the performed activities on the template paper, provided by the coordinator.

3. Article – Project activities

Partner must perform activities in agreed time frame, which is determined by coordinator in communication with partner. The time frame must be in compliance with main project deadlines and deliverables, as follows:

| Deliverable | Deadline | Reference to contract (Contracting form) |
| --- | --- | --- |
| Title (whole or part of the deliverable?) | Date | R1 |

4. Article – Respect for LLP rules

Partner agrees on the content of the project and his participation in it, agreeing at the same time on all the conditions that the Leonardo da Vinci / Lifelong learning programme prescribes in terms of financial, administration and work quality requirements (Guidelines for administrative and financial management, as issued by the European Commission for year 2009).

Failing to fulfill any of above mentioned fields of responsibility could mean that the partner did not fulfill his duties and is therefore not eligible to financial refund for the costs of activities for which the conditioned were not fulfilled.

5. Article – Budget structure

Coordinator and partner agree that the common budget for the project is xxx.xx, 00 EUR, of which the partner’s share equals the following amounts per cost category:

| COSTS | Total project value | Grant total (up to 75%) |
| --- | --- | --- |
| A. DIRECT COSTS | 18.589 | 13.942 |
| 1. Staff costs | 11.060 | 8.295 |
| 2. Travel&subsistance | 6.340 | 4.755 |
| 3. Equipment | 650 | 488 |
| 4. Subcontracting | 0 | 0 |
| 5. Other | 540 | 405 |
| B. INDIRECT COSTS | 1.291 | 968 |
| TOTAL | 19.881 | 14.910 |

6. Article – Reporting and Payment

It is agreed that partner will receive the first payment on 15. th of February covering the costs of activities on the project for December 2007 and January 2008.

Partners must therefore send the request for payment and supportive documentation till 5th of February.

Further payments will be made on a three month period basis and will be based on correct administrative documentation sent by partner to coordinator.

Payments will be transferred in a period of 20 days from receipt of the request for payment document and all necessary supportive documentation.

Partners must therefore send the request for payment, activities reports and supportive documentation till 8th day of the month, following the conclusion of 3 month period as follows:

| PERIOD | DEAD LINE FOR REPORTS |
| --- | --- |
| December 07 – January 08 | Latest by 8. of February 08 |
| February 08 - April 08 | Latest by 8. of May 08 |
| May 08 - July 08 | Latest by 8. of August 08 |
| 1. August 08 - 31. Avgust 08 | Latest by 8. of September 08 (due to interim report) |
| September 08 – November 08 | Latest by December 08 |
| December 08 – Februar 09 | Latest by 8. of March 09 |
| March 09 – May 09 | Latest by 8. of June 09 |

All costs must be eligible and in compliance with special conditions, which are attached as annex to this contract.

Payment will be transferred on the bank account of partner, stated on the request for payment document.

Payments will be only made if partner has finished agreed activities and costs stated in the documentation are eligible and are calculated in accordance to LLP programme administrative rules.

7. Article – Project coordination

Partner agrees to fulfill the activities assigned by the coordinator. The coordinator will prepare a three month action plan throughout the whole period of project duration, therefore assuring that all activities will be performed on time and with consistency to quality and financial requirements.

Responsible person for the project at project coordinator is predstavnik koordinatorja

Responsible person for the project at the partner is predstavnik partnerja.

8. Article - Responsibilty

Partner is free of responsibility for fulfillment of further assigned tasks if coordinator fails to refund the costs incurred. Partner is not eligible to receive refund of costs incurred if activities were not performed within agreed time frame or quality.

9. Article – Reporting to the funding agency

Partner agrees that coordinator takes full responsibility of correct administrative and financial reporting to the CMEPIUS agency as follows:

- Interim report for the period 3.12.07 – 3.9.08: latest by 30.10.08

- Final report for the whole period of project: latest by 3.8.2009

It is however of partners duty to send correct documentation and activities reports on time, as agreed with project coordinator.

The coordinator does not take the responsibility if agreed activities were not performed by the partner, except force majeure. Vice versus partner does not take over the responsibility if he has correctly finished all agreed activities, but the coordinator failed to fulfill its responsibility toward CMEPIUS National agency from any reason, except force majeure.

10. Article – Property rights

Parties agree that all results of the project in English and Slovenian language belong to the project coordinator and all results of the project in XXX language belong to the partner. Partner is allowed to explore intellectual property rights in English or Slovenian language of the project for results dissemination during and after the project with written permission of the coordinator.

11. Article – Further arrangements

Any additional issues that would arise during project execution will be agreed with annex to this contract.

12. Article – Settlement of disputes

All disputes that could arise from this contract will be settled harmoniously between partners. If however, disputes could not be settled harmoniously, the agreement will be achieved on the court of law at: Okrožno sodišče v xxx, Slovenia.

13. Article - Validity

This contract is issued in two originals, one per each party. It is valid after both authorized representatives of each institution sign it.

| Date Coordinator institution Signature of legal representative | Date Partner institution Signature of legal representative |
| --- | --- |

# Text boxes

PRIČUJOČI OBRAZEC JE PRIPOMOČEK; KI GA POSREDUJE NACIONALNA AGENCIJA IN V NIČEMER NI ODGOVORNA ZA MOREBITNE NAPAKE ALI ZAPLETE, KI BI IZHAJALE IZ TEGA OBRAZCA.